## 5-Year Cap Financing Plan
Sample 5-Year Capital Project Financing Plan
Project: Library Renovation and Expansion
Total Estimated Cost: $3,000,000
Project Budget
Project Component | Cost
Architectural & Engineering Services | 250000
Site Work | 150000
Building Renovation | 1000000
Building Addition | 1000000
Furniture, Fixtures & Equipment | 250000
Technology Infrastructure | 100000
Contingency | 250000
Total Project Cost | 3000000
Sources of Funds
Funding Source | Amount | % of Total
Capital Reserve Fund | 500000 | 16.67%
NYS Public Library Construction Aid | 250000 | 8.333%
Municipal Contribution | 750000 | 25%
Capital Campaign / Private Donations | 750000 | 25%
Foundation & Corporate Grants | 500000 | 16.67%
Friends of the Library | 250000 | 8.333%
Total Sources | 3000000 | 100%
Funding Timeline
Fiscal Year | Activity | Funding Source | Amount
Year 1 | Building Needs Assessment & Planning | Capital Reserve | 50000
Year 1 | Architectural Design | Capital Reserve | 200000
Year 2 | Detailed Design & Engineering | Capital Reserve | 250000
Year 2 | Grant Awards Received | NYS Construction Aid | 500000
Year 2 | Capital Campaign Launch | Private Donations | 250000
Year 3 | Construction Begins | Municipal Contribution | 500000
Year 3 | Construction Continues | NYS Construction Aid | 500000
Year 3 | Capital Campaign Receipts | Private Donations | 250000
Year 4 | Construction Completion | Municipal Contribution | 250000
Year 4 | Capital Campaign Receipts | Private Donations | 250000
Year 4 | Grants & Friends Contributions | Grants/Friends | 500000
Year 5 | Project Closeout & Furnishings | Remaining Funds | 250000

## 5-Year Cap Improvement Plan
Library Capital Improvement Plan (2027-2031) | [6 empty] | Five-Year Capital Plan Summary
Priority* | Project | Description | Estimated Cost | Potential Funding Source(s) | Target Year | Status | Year | Estimated Investment
High | Roof Replacement | Replace aging roof nearing end of useful life | 250000 | Capital Reserve, NYS Construction Aid | 2027 | Planned | 2027 | 600000
High | HVAC Replacement | Upgrade heating and cooling systems for efficiency and reliability | 350000 | NYS Construction Aid, Municipal Support | 2027 | Planned | 2028 | 200000
High | ADA Restroom Renovation | Improve accessibility and code compliance | 125000 | NYS Construction Aid, Capital Reserve | 2028 | Planned | 2029 | 300000
High | Fire Alarm System Upgrade | Replace outdated life safety equipment | 75000 | Capital Reserve | 2028 | Planned | 2030 | 135000
Medium | Public Meeting Room Renovation | Improve flexibility and technology capabilities | 200000 | Construction Aid, Private Donations | 2029 | Planned | 2031 | 200000
Medium | Parking Lot Resurfacing | Repair pavement and improve drainage | 100000 | Municipal Support, Capital Reserve | 2029 | Planned | Total | 1435000
Medium | Interior Lighting Conversion | Convert to LED fixtures and controls | 60000 | Energy Grants, Capital Reserve | 2030 | Planned
Low | Furniture Replacement | Replace aging public seating and tables | 75000 | Friends of the Library, Donations | 2030 | Planned
Low | Outdoor Reading Garden | Create outdoor programming space | 150000 | Private Fundraising, Grants | 2031 | Planned
Low | Children's Area Refresh | Improve furnishings and shelving | 50000 | Friends, Donations | 2031 | Planned
Priority Definitions*
High Priority
Life safety concerns
Building systems at end of useful life
Code or accessibility compliance requirements
Projects needed within 1-2 years
Medium Priority
Projects that improve service delivery, efficiency, or building condition
Projects needed within 3-5 years
Low Priority
Desirable improvements and enhancements
Projects that may be deferred beyond 5 years if necessary